## 008 August
Line | Item name | Quantity | Price | Amount | Date | Work note
1 | Dashboard Updates | 2 | 250 |  | 8/11/2026 | Rebranded report and app with Visit Dana Point photography, logos, and coastal palette; fixed hosting build for PDF export
2 | Synced all data source | 2 | 250 |  | 8/11/2026 | Refreshed STR, CoStar, and Datafy data through 8/1/2026; ingested August Datafy export
3 | Dashboard Updates | 1 | 250 |  | 8/11/2026 | Replaced placeholder CoStar chain-scale and competitive-set figures with real submarket report data; set CoStar views to YTD 2026
4 | Dashboard Updates | 2 | 250 |  | 8/11/2026 | Chart readability pass, header redesign, and pop-out viewer for each report section
5 | Dashboard Updates | 1 | 250 |  | 8/11/2026 | Added Summarize button and in-app help guide
6 | Setup Alerts | 1 | 250 |  | 8/11/2026 | Built admin email send and moved delivery to SendGrid API; styled Download PDF button
7 | Automate Processes | 1 | 250 |  | 8/14/2026 | Set up weekly Thursday STR auto-sync
8 | Automate Processes | 2 | 250 |  | 8/14/2026 | Compiled Heather's dashboard requirements; built CoStar export script and Datafy download reminder
9 | Power BI Build | 2 | 250 |  | 8/14/2026 | Built Power BI data package (eight export tables) and Power BI build guide
10 | Created Dashboard | 3 | 250 |  | 8/15/2026 | Hosted Heather's build on Railway; added notes layer, Ask-the-Data tool, and report archive
11 | Dashboard Updates | 2 | 250 |  | 8/16/2026 | Fixed cut-off recommendation text in PDF report; rebuilt simplified view on the PULSE design
12 | Dashboard Updates | 4 | 250 |  | 8/17/2026 | Added Intelligence Brief, notes, report archive, native charts, map, period selector, and flipbook to live app; restructured PDF to one category per page
13 | Client Meeting | 1 | 250 |  | 8/19/2026 | Meeting with Heather to review build
14 | Automate Processes | 2 | 250 |  | 8/19/2026 | Built on-demand STR sync button and full sync workflow
15 | Planning and Coordination | 1 | 250 |  | 8/20/2026 | Outlined Power Automate licensing and SharePoint access requirements for Visit Dana Point
16 | Data Review | 2 | 250 |  | 8/28/2026 | Reviewed new Datafy advertising exports; mapped six new report types and duplicate files before load
17 | Dashboard Updates | 5 | 250 |  | 8/31/2026 | Added live section visuals, feeder-market map, Market Performance and Forward Outlook sections, and section-picker PDF export

## 009 September
Line | Item name | Quantity | Price | Amount | Date | Work note
1 | Synced all data source | 3 | 250 |  | 9/9/2026 | Integrated new STR, CoStar, and Datafy data; added CoStar segmentation and Datafy advertising visuals
2 | Data Review | 4 | 250 |  | 9/19/2026 | Audited all CoStar files and report types; fixed CoStar loaders; limited CoStar views to Dana Point real data; planned Power Automate intake
3 | Automate Processes | 3 | 250 |  | 9/20/2026 | Prepared CoStar automation (file routing, freshness check, sync script, schedule); verified live deployment
4 | Automate Processes | 3 | 250 |  | 9/21/2026 | Built CoStar portal fetch script with download validation and workflow; reviewed dashboard design references
5 | Dashboard Updates | 2 | 250 |  | 9/24/2026 | Dashboard updates: brand tokens, real-data Group Intelligence views, and app refinements
6 | Dashboard Updates | 3 | 250 |  | 9/25/2026 | Redesigned board view for Heather's Board of Directors: key question per section, dynamic summaries, mobile layout
7 | Dashboard Updates | 4 | 250 |  | 9/29/2026 | Built new board visuals and data-quality documentation; published update to live site
8 | Dashboard Updates | 1 | 250 |  | 9/30/2026 | Verified live site on desktop and mobile; fixed outdated event insight

## Held for October
Line | Item name | Quantity | Price | Amount | Date | Work note
1 | Automate Processes | 3 | 250 |  | 10/1/2026 | Built weekly recap automation for Heather (Thursday data check, Friday report draft); enabled Thursday STR sync
2 | Synced all data source | 2 | 250 |  | 10/1/2026 | Loaded latest CoStar and Datafy data; added date-range handling for Datafy files
3 | Automate Processes | 0.5 | 250 |  | 10/2/2026 | Refined weekly recap report
4 | Automate Processes | 2 | 250 |  | 10/7/2026 | Moved STR source to Visit Dana Point SharePoint; set on-demand refresh process and CoStar upload step
5 | Synced all data source | 3 | 250 |  | 10/8/2026 | Pulled all Datafy modules; refreshed STR, CoStar, and Datafy data; ran app audit; documented fetch runbook
6 | Weekly Report | 1 | 250 |  | 10/8/2026 | Prepared weekly PULSE report for Heather